## Product Backlog
Product Name: | StickJumpForce
Name: | TeamX
Total Features | Left | Available | Completed | Sprint Ends
Start | 28 | 28 | 0
Sprint 1 | 28 | 28 |  | 2018-10-04
Sprint 2 | 28 | 28 |  | 2018-10-11
Sprint 3 | 28 | 28 |  | 2018-10-25
Sprint 4 | 28 | 28 |  | 2018-11-08
Sprint 5 | 28 | 28 |  | 2018-11-15
Sprint 6 | 28 | 28 |  | 2018-12-03
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | We want to… | For… | Notes | RERENCES
INC1.1 | 1 | NS | 1 |  | Create UML Diagrams | Increment I
INC1.2 | 2 | NS | 1 |  | Complete and submit Increment I | Increment I |  | Status Annotations
DSG1 | 3 | NS | 1 |  | Create foreground sprites | Environment design |  | NS | Not started
DSG2 | 4 | NS | 1 |  | Create background sprites | Environment design |  | S | Started
DSG3 | 5 | NS | 1 |  | Create midground sprites | Environment design |  | COM | Completed
DSG4 | 6 | NS | 1 |  | Create farground sprites | Environment design
TUT1 | 7 | NS | 1 |  | Phase I level development | Environment design |  | Feature ID
LEV1.1 | 8 | NS | 1 |  | Setup UNITY | Getting started | Complete tutorial section 1-3
TUT2 | 9 | NS | 2 |  | Complete tutorial section 4 | Environment design |  | INC | Increment
LEV1.2 | 10 | NS | 2 |  | Phase II level development | Environment design |  | DSG | Design
| 11 | NS | 2 |  |  |  |  | TUT | Tutorial
AI1 | 12 | NS | 3 |  | Create character sprites | Player setup |  | LEV | Level
TUT2 | 13 | NS | 3 |  | Complete tutorial section 5 | Player setup |  | AI | AI system
AI2 | 14 | NS | 3 |  | Create enemy sprites | Enemy AI
TUT3 | 15 | NS | 3 |  | Complete tutorial section 6 | Enemy AI
TUT4 | 16 | NS | 3 |  | Complete tutorial section 7 | Game system
| 17 | NS | 3
INC2 | 18 | NS | 4 |  | Complete and submit Increment II | Increment II
TUT5 | 19 | NS | 4 |  | Complete tutorial section 8 | Game system
TUT6 | 20 | NS | 4 |  | Complete tutorial section 9 | Game system
TUT7 | 21 | NS | 4 |  | Complete tutorial section 10 | Game system
| 22 | NS | 4
INC3 | 23 | NS | 5 |  | Complete and submit Increment III | Increment III
TUT8 | 24 | NS | 5 |  | Complete tutorial section 11 | Game publishing
INC4 | 25 | NS | 5 |  | Presentation preparation | Increment IV
| 26 | NS | 5
INC4 | 27 | NS | 6 |  | Complete presentation and deliver | Increment IV
INC4 | 28 | NS | 6 |  | Final product delivery | Increment IV

## Sprint 1
Sprint # | 1
Start on | 2018-09-28
End on | 2018-10-04
Total Task | 21
Date | Task Left
28 | 20
29 | 21
30 | 21
1 | 21
2 | 21
3 | 21
4 | 21
Task ID | Feature ID | Assigned To | Description | Status | Notes | RERENCES
1 | INC1.1 | Bhuwan | UML-Menu system | S
2 | INC1.1 | Diptin | UML-AI | NS |  | Status Annotations
3 | INC1.1 | Haris | UML-Graphics | COM |  | NS | Not started
4 | INC1.1 | Haris | UML-Upgrades and inventories | COM |  | S | Started
5 | INC1.1 | Cristian | UML-Character movement | NS |  | COM | Completed
6 | INC1.1 | Cristian | Context diagram | NS
7 | INC1.1 | Cristian | System class diagram | NS |  | Feature ID
8 | INC1.2 | Cristian | Compile and print the UML diagrams | NS |  | INC | Increment
9 | DSG1 | Josue | Design some street items like trash-can, street-bench, etc. | NS |  | DSG | Design
10 | DSG1 | Diptin | Design street lights and exit door for level completion | NS |  | TUT | Tutorial
11 | DSG2 | Bhuwan | Design soil, brick, surface, and small buildings | S |  | LEV | Level
12 | DSG3 | Josue | Design different buildings and city like structures | NS |  | AI | AI system
13 | DSG3 | Haris | Design different buildings and city like structures | NS
14 | DSG4 | Haris | Design some twinkling stars frames | NS
15 | DSG4 | Josue | Design night mode | NS
16 | DSG4 | Cristian | Design a moon | NS
17 | LEV1.1 | Bhuwan | Use provided sprites for level development | NS
18 | TUT1 | Bhuwan | Setup Unity and complete section 1-3 | COM
19 | TUT1 | Haris | Setup Unity and complete section 1-3 | S
20 | TUT1 | Diptin | Setup Unity and complete section 1-3 | NS
21 | TUT1 | Cristian | Setup Unity and complete section 1-3 | NS
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Initials Here | Update UML to match new methods if changed | NS - Not Started
N + 1 | BN | Initials Here | Add methods to Bundle and derived classes | NS - Not Started
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | NS - Not Started

## Sprint 2
Sprint # | 2
Start on | 2018-04-02
End on | 2018-04-08
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 3
Sprint # | 3
Start on | 2018-04-09
End on | 2018-04-15
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 4
Sprint # | 4
Start on | 2018-04-16
End on | 2018-04-22
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 5
Sprint # | 5
Start on | 2018-04-23
End on | 2018-04-29
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes