## Product Backlog
Product Name: | StickJumpForce
Name: | TeamX
Total Features | Left | Completed | Sprint Ends
Start | 28 | 0
Sprint 1 | 26 | 2 | 2018-10-04
Sprint 2 | 19 | 7 | 2018-10-11
Sprint 3 | 19 |  | 2018-10-26
Sprint 4 | 19 |  | 2018-11-09
Sprint 5 | 19 |  | 2018-11-16
Sprint 6 | 19 |  | 2018-12-03
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | We want to… | For… | Notes | REFERENCES
INC1.1 | 1 | COM | 1 | 1 | Create UML Diagrams | Increment I
INC1.2 | 2 | NS | 1 | 1 | Complete and submit Increment I | Increment I |  | Status Annotations
DSG1 | 3 | NS | 1 | 2 | Create foreground sprites | Environment design |  | NS | Not started
DSG2 | 4 | NS | 1 | 2 | Create background sprites | Environment design |  | S | Started
DSG3 | 5 | NS | 1 | 2 | Create midground sprites | Environment design |  | COM | Completed
DSG4 | 6 | NS | 1 | 2 | Create farground sprites | Environment design |  |  | Updated
LEV1.1 | 7 | NS | 1 | 2 | Phase I level development | Environment design
TUT1 | 8 | NS | 1 | 2 | Setup UNITY | Getting started | Complete tutorial section 1-3 | Feature ID
TUT2 | 9 | NS | 2 | 2 | Complete tutorial section 4 | Environment design
LEV1.2 | 10 | NS | 2 |  | Phase II level development | Environment design |  | INC | Increment
INC2.1 | 11 | NS | 2 |  | SRA planning | Increment II |  | DSG | Design
AI1 | 12 | NS | 3 |  | Create character sprites | Player setup |  | TUT | Tutorial
TUT2 | 13 | NS | 3 |  | Complete tutorial section 5 | Player setup |  | LEV | Level
AI2 | 14 | NS | 3 |  | Create enemy sprites | Enemy AI |  | AI | AI system
TUT3 | 15 | NS | 3 |  | Complete tutorial section 6 | Enemy AI
TUT4 | 16 | NS | 3 |  | Complete tutorial section 7 | Game system
DSG5 | 17 | NS | 3 |  | Design additional sprites | Game design
INC2.2 | 18 | NS | 4 |  | Complete and submit Increment II | Increment II
TUT5 | 19 | NS | 4 |  | Complete tutorial section 8 | Game system
TUT6 | 20 | NS | 4 |  | Complete tutorial section 9 | Game system
TUT7 | 21 | NS | 4 |  | Complete tutorial section 10 | Game system
| 22 | NS | 4
INC3 | 23 | NS | 5 |  | Complete and submit Increment III | Increment III
TUT8 | 24 | NS | 5 |  | Complete tutorial section 11 | Game publishing
INC4 | 25 | NS | 5 |  | Presentation preparation | Increment IV
| 26 | NS | 5
INC4 | 27 | NS | 6 |  | Complete presentation and deliver | Increment IV
INC4 | 28 | NS | 6 |  | Final product delivery | Increment IV

## Sprint 1
Sprint # | 1
Start on | 2018-09-28
End on | 2018-10-04
Total Task | 21
Date | Task Left
28 | 20
29 | 19
30 | 18
1 | 17
2 | 13
3 | 12
4 | 10
Task ID | Feature ID | Assigned To | Description | Status | Notes | REFERENCES
1 | INC1.1 | Bhuwan | UML-Menu system | COM
2 | INC1.1 | Diptin | UML-AI | COM |  | Status Annotations
3 | INC1.1 | Haris | UML-Graphics | COM |  | NS | Not started
4 | INC1.1 | Haris | UML-Upgrades and inventories | COM |  | S | Started
5 | INC1.1 | Cristian | UML-Character movement | COM |  | COM | Completed
6 | INC1.1 | Cristian | Context diagram | COM |  |  | Updated
7 | INC1.1 | Cristian | System class diagram | COM |  |  | Stalled
8 | INC1.2 | Cristian | Compile and print the UML diagrams | COM
9 | DSG1 | Josue | Design some street items like trash-can, street-bench, etc. | COM |  | Feature ID
10 | DSG1 | Diptin | Design street lights and exit door for level completion | S |  | INC | Increment
11 | DSG2 | Bhuwan | Design soil, brick, surface, and small buildings | S |  | DSG | Design
12 | DSG3 | Josue | Design different buildings and city like structures | COM |  | TUT | Tutorial
13 | DSG3 | Haris | Design different buildings and city like structures | NS |  | LEV | Level
14 | DSG4 | Haris | Design some twinkling stars frames | NS |  | AI | AI system
15 | DSG4 | Bhuwan | Design night mode | COM
16 | DSG4 | Cristian | Design a moon | NS
17 | LEV1.1 | Bhuwan | Use provided sprites for level development | S
18 | TUT1 | Bhuwan | Setup Unity and complete section 1-3 | COM
19 | TUT1 | Haris | Setup Unity and complete section 1-3 | COM
20 | TUT1 | Diptin | Setup Unity and complete section 1-3 | COM
21 | TUT1 | Cristian | Setup Unity and complete section 1-3 | S
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Initials Here | Update UML to match new methods if changed | NS - Not Started
N + 1 | BN | Initials Here | Add methods to Bundle and derived classes | NS - Not Started
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | NS - Not Started

## Sprint 2
Sprint # | 1
Start on | 2018-10-05
End on | 2018-10-12
Total Task | 17
Date | Task Left
4 | 16
5 | 16
6 | 16
7 | 15
8 | 15
9 | 15
10 | 15
11 | 15
12 | 3
Task ID | Feature ID | Assigned To | Description | Status | Notes | REFERENCES
1 | TUT1 | Haris | Setup Unity and complete section 1-3 | COM
2 | TUT1 | Cristian | Setup Unity and complete section 1-3 | COM |  | Status Annotations
3 | TUT2 | Diptin | Complete tutorial section 4: Building the environment | x |  | NS | Not started
4 | TUT2 | Cristian | Complete tutorial section 4: Building the environment | x |  | S | Started
5 | TUT2 | Haris | Complete tutorial section 4: Building the environment | x |  | COM | Completed
6 | TUT2 | Bhuwan | Complete tutorial section 4: Building the environment | COM |  |  | Updated
7 | DSG1 | Bhuwan | Design some street lights and spikes | COM |  |  | Stalled
8 | DSG1 | Diptin | Design street bench and exit door for level completion | S |  | X | Cancelled
9 | DSG2 | Bhuwan | Design soil, brick, surface, and small buildings | COM
10 | DSG3 | Josue | Design dumpster, some trees and 2 tall building for midground | S |  | Feature ID
11 | DSG3 | Haris | Design 5 different sized buildings | COM |  | INC | Increment
12 | DSG4 | Haris | Design twinkling stars (2 frames) | COM |  | DSG | Design
13 | DSG4 | Cristian | Design a moon | COM |  | TUT | Tutorial
14 | DSG4 | Cristian | Design 3 different sized buildings | COM |  | LEV | Level
15 | LEV1.1 | Bhuwan | Use provided sprites for level development | COM |  | AI | AI system
16 | LEV1.1 | Josue | Design the overview of level 1 | COM
17 | INC2.1 | Diptin | Plan SRA increment and form tasks list
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Initials Here | Update UML to match new methods if changed | NS - Not Started
N + 1 | BN | Initials Here | Add methods to Bundle and derived classes | NS - Not Started
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | NS - Not Started

## Sprint 3
Sprint # | 1
Start on | 2018-10-13
End on | 2018-10-26
Total Task | 18
Date | Task Left
13 | 28
14 | 28
15 | 28
16 | 28
17 | 28
18 | 28
19 | 28
20 | 27
21 | 26
22 | 26
23 | 24
24 | 24
25 | 24
26 | 24
Task ID | Feature ID | Assigned To | Description | Status | Notes | REFERENCES
1 | INC2.1 | Diptin | Plan SRA increment and form tasks list | COM
2 | DSG1 | Diptin | Design street bench and exit door for level completion |  |  | Status Annotations
3 | DSG3 | Josue | Design dumpster, some trees and 2 tall building for midground | COM |  | NS | Not started
4 | TUT2 | Bhuwan | Complete tutorial section 5 | S |  | S | Started
5 | TUT2 | Diptin | Complete tutorial section 5 |  |  | COM | Completed
6 | TUT2 | Cristian | Complete tutorial section 5 |  |  |  | Updated | "These two are references for me!" -Bhuwan
7 | TUT2 | Haris | Complete tutorial section 5 | S |  |  | Stalled
8 | LEV1.2 | Bhuwan | Complete Level 1 design | S |  | X | Cancelled
9 | DSG5 | Haris | Design sprites for weapons
10 | DSG5 | Cristian | Design sprites for health potions and XP |  |  | Feature ID
0 |  |  | COMPLETE UNTIL HERE BY FRIDAY 10/19 |  |  | INC | Increment
11 | INC2.2 | Cristian | Character movement requirements |  |  | DSG | Design
12 | INC2.2 | Haris | Graphics, and Inventories/Upgrades requirements |  |  | TUT | Tutorial
13 | INC2.2 | Bhuwan | Menu System Requirements | COM |  | LEV | Level
14 | INC2.2 | Diptin | AI requirement |  |  | AI | AI system
15 | INC2.2 | Cristian | 5) Software process and UML Diagrams
16 | INC2.2 | Bhuwan | 7) Delovery and Schedule | COM
17 | INC2.2 | Haris | 6)Assumptions and constraints
18 | INC2.2 | Diptin | Finalize and complete every requirements and combine
19 | A1 | Josue | Sketch and design main character
20 | A2 | Diptin | Sketch and design enemy characters
21 | A1 | Bhuwan | Make sprites for main character
22 | A1 | Cristian | Make sprites for main character
23 | A2 | Bhuwan | Make sprites for enemy characters
24 | A2 | Haris | Make sprites for enemy characters
25 | TUT2 | Diptin | Complete tutorial section 6
26 | TUT2 | Bhuwan | Complete tutorial section 6
27 | TUT2 | Cristian | Complete tutorial section 6
28 | TUT2 | Haris | Complete tutorial section 6
29 | TUT3 | Diptin | Complete tutorial section 7
30 | TUT3 | Bhuwan | Complete tutorial section 7
31 | TUT3 | Cristian | Complete tutorial section 7
32 | TUT3 | Haris | Complete tutorial section 7
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Initials Here | Update UML to match new methods if changed | NS - Not Started
N + 1 | BN | Initials Here | Add methods to Bundle and derived classes | NS - Not Started
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | NS - Not Started